## Slide 1
Tyler Financials
Project Update

## Slide 2
Introduction
CCWD’s Finance and Human Resources Departments kicked off the Core Financials and Payroll/Personnel Management Implementation through Tyler Technologies at the end of July. This part of the implementation is a follow-up to the Utility Billing (UB) and Accounts Receivable modules that went live in September 2021. Once this part of the implementation is complete, all Tyler modules will be integrated with each other.

## Slide 3
Project Overview
CCWD’s internal project team comprised of a steering committee, project manager, technical lead(s), and change management lead(s) are members of the organization who are familiar with and actively support the mission of the project. It is common for individuals to serve in multiple roles.
Establish CCWD’s functional leaders who are authorized to make procedural decisions within their department. Establish CCWD power users who are the experts in their field and are responsible for providing insight to current processes and ensure the configuration in the Tyler system are the most efficient.
The CCWD team will work with the Tyler team to implement all Core Financial and Payroll/Personnel Management modules during the key block implementation phases, culminating in an integrated system that brings together the UB, Finance and Human Resources departments.

## Slide 4
Key Milestones
Current/Future State Analysis Meetings
Meetings between CCWD project team members and the Tyler Implementation Consultant to discuss current processes and start making decisions about how these will run within the Tyler environment.
Core Financials Block Implementation
(3-4 weeks)
Configuration, training, testing and final data push to go live in the Core Financials, Purchasing, and Bank Reconciliation modules in Tyler.
Payroll Block Implementation
(5-7 weeks)
Configuration, training, testing, parallel payroll processing, and final data push to go live in the Personnel Management and Employee Access Pro modules in Tyler.
Ancillary Implementation
(2 weeks)
Current/future state analysis, configuration and training to go live in the ESS Time & Attendance, Fixed Assets, Project Accounting and Budgeting modules in Tyler.

## Slide 5
Timeline Diagram
Stage 1: Initiate & Plan
Stage 2: Assess & Define
Stage 3: Prepare Solution
Stage 4: Production Readiness
Stage 5: Production
Stage 6: Close
Completed - September
Completed - September
Completed - November
Pending
Pending
Pending

## Slide 6
04
Phase
Production Readiness
  Solution Validation
  Go Live Readiness
  End User Training

## Slide 7
05
Phase
Production
  GO LIVE
  Transition to Client Services
  Post-Go Live Activities

## Slide 8
06
Phase
Close
  Phase Close Out
  Project Close Out
  Administrative Project Closure

## Slide 9
Training
LEARNING
THE BASICS
Dashboard Use
Add Favorites
Schedule A Report
Grid Customization
CONFIGURATION TRAINING
Add a New GL Account
Add a New Vendor
Set Up a New Deduction
Add a New Bank Account
END USER
TRAINING
Post a Journal Entry
Enter a Payable
Process Payroll
Reconcile a Bank Account
POST-PRODUCTION
TRAINING
Enter a Budget
Fiscal Year End Process
Process W2s
Payroll Corrections

## Slide 10
Core Financials
Completed
Working with Tyler’s Transitional Services Team to further dial in processes, configuration on Core Financials
Currently configuring Project Accounting Module
Post-Go Live training pending
Ancillary Budget Module pending implementation
Personnel Management & Employee Time/Attendance
Pending Completion
Go Live for Payroll and Time/Attendance has been pushed slightly, revised to middle of January 2025
Training of all CCWD employees on Employee Self Service time & attendance platform pending
Status Update

## Slide 11
Thank
You